## Sheet1
Enrollment Management Annual Work Plan 2019-2020
Enrollment Strategies
Action | Lead(s) | EMP Goal | Resource Needs | Retention | Scheduling | Marketing | Technology | Curriculum | Emerging Programs | Noncredit | Dual Enrollment | Incumbent Workers | Adult Learners
Computer Science courses offered, and Civic Engagement moving through curriculum and should be offered fall 2020 | Curriculum Co-chairs, Program Specific Deans, faculty level | SD1.A.1: Associate Degrees for Transfer available—increase from 29 in 2018-2019 to 31 by 2023- 2024 | Dean of Emerging Programs, Admin Assistant for Dean, Faculty for newly approved programs |  |  |  |  | X | X
Physics and Chemistry will establish UC Pathways | Department Chairs of Physics and Chemistry, Curriculum co-chair, Articulation Officer, Deans | SD1.A.3: Degrees aligned with new UC pathways—increase to 5 by 2023-2024 | n/a |  |  |  |  | X
Will complete curricular approval process and offer courses spring or fall 2020 for Engineering, Cybersecurity, Cloud, Data Science, Computer Science, Commercial Dance, GIS, Vet Tech. Partner with Adult Ed programs to offer program and GE for Respiratory Therapy and Surgical Tech. | Deans and Chairs of respective areas | SD1.B.1: CTE degrees and certificates available—increase from 29 in 2018-2019 to 34 by 2023-2024 | Dean of Emerging Programs, Admin Assistant for Dean, Faculty for newly approved programs |  |  |  |  | X | X |  |  | X | X
Will complete curricular approval process and offer courses for career exploration badge by spring 2020 | CTE Counselor and Career Transfer Center | SD1.B.2: CTE alternative credentials available such as digital badges that lead to certificates — increase from 50 in 2018-2019 to 100 by 2023-2024 | Dean of Emerging Programs, Admin Assistant for Dean | [5 empty] | X | X
Establish program in Biotech, Applied Manufacturing, Engineering by spring 2020. | Career Transfer Center | SD1.B.3: Pre-apprenticeship programs—increase to 3 by 2023-2024 | Dean of Emerging Programs, Admin Assistant for Dean | [5 empty] | X |  |  | X
Using funds from the CVC-OEI grant, complete online programming for Child Development, Business, Accounting, Hospitality, and Public Relations/Journalism | Deans and Chairs of respective areas, and Dean of DE | SD1.C.1: Degrees, certificates, and proficiency awards able to be earned fully online—increase to 35 by 2023-2024 | n/a |  | X |  | X
Will complete curricular approval process and offer courses for Entrepreneurship, Career, Theater Lighting, Landscape and Wine for Hospitality by spring 2020 | Deans and Chairs of respective areas | SD1.D.1: Noncredit courses for professional improvement—increase from 3 in 2018-2019 to 25 by 2023-2024 | Dean of Emerging Programs, Admin Assistant for Dean, Faculty for newly approved programs | [5 empty] | X | X |  | X | X
In alignment with the Student Equity Plan, enhance tutoring services, connect more students with a student success coach, increase awareness of mental health and professional development for faculty, increase usage of ZTC/OER, provide high impact equity training for faculty. Implement Starfish. Contact students who dropped and get them re-enrolled for spring. | Dean of Counseling, Student Health Director, Dean of Distance Education, Dean of Professional Development, Director of IT, Director of Outreach | SD1.E.1: Fall to spring persistence rates—decrease equity gaps for disproportionately impacted groups by 40% by 2023-2024, and fully close achievement gaps by 2026-2027 | Additional Starfish features, counseling hours | X |  |  | X
Complete curriculum process for Math M11 and M12 and 900 support courses and offer courses by fall 2020 in compliance with AB705. | Dean and Chair of Math | SD1.E.2: Completion of transfer-level math and English in first year—decrease equity gaps for disproportionately impacted groups by 40% by 2023-2024, and fully close achievement gaps by 2026-2027 | Faculty for Math and English |  |  |  |  | X
Call students who applied but did not enroll. Also, for students who applied but did not enroll in Business, ECE, and Computer Science, contact those student through various marketing channels including email and Facebook to see if the PACE program could be a better fit for their schedules. | Director of Outreach and International Relations | SD2.A.1: Percentage of applicants that successfully enroll—decrease equity gaps for disproportionately impacted groups by 40% by 2023-2024, and fully close achievement gaps by 2026-2027 | Dean of Emerging Programs, Admin Assistant for Dean, Marketing Specialist |  |  | X |  |  | X |  |  |  | X
Continue to expand dual enrollment course offerings. Expand CCAP MOU to two additional HS districts. Optimize operations and scheduling. Establish workgroup to optimize student/faculty success. | Dean of Dual Enrollment, Deans and Chairs of respective areas, Academic Senate President | SD2.B.3: Dual enrollment students—Increase from 579 in fall 2017 to 707 by fall 2023 | Dean of Emerging Programs, Admin Assistant for Dean, Outreach Specialist, Faculty for Math and English and dual enrollment |  | X |  |  |  | X |  | X
Provide two additional DE certification training sessions. Offer more sections of DE. Collect data on new DE courses to monitor student success. Establish Math testing center. | Dean of Distance Education, Deans and Chairs of respective areas, Academic Senate President | SD2.C.1: Distance education FTES—increase offerings from 1,571 in 2017-2018 to 3,189 by 2023- 2024 | n/a |  | X |  | X
Add 6 Saturday hybrid sections as part of PACE | Dean of PACE, Deans and Chairs of respective areas, Academic Senate President | SD2.C.2: Friday, weekend, and evening sections—increase as total from 340 in fall 2018 to 406 by fall 2023 | Dean of Emerging Programs, Admin Assistant for Dean, Counseling Assistant hours, Counseling hours, Marketing Specialist |  | X | X |  |  | X |  |  |  | X
Add 44 short term sections as part of PACE | Dean of PACE, Deans and Chairs of respective areas, Academic Senate President | SD2.C.3: Short term sections—increase from 249 in fall 2018 to 304 by fall 2023 | Dean of Emerging Programs, Admin Assistant for Dean, Counseling Assistant hours, Counseling hours, Marketing Specialist |  | X | X |  |  | X |  |  |  | X
It will be several more years before a decision is made on compressed calendar. Meantime, we will explore offering a winter 4 week session. | Deans and Chairs of respective areas, Academic Senate President | SD2.C.4: Offer a winter intersession by 2023 (if district switches to compressed calendar) | n/a |  | X
Continue activities for the 15 to finish campaign including contacting students who enrolled in 12 or more units. Measure effectiveness of campaign. Explore whether a campaign for 30 to finish may be more effective adding in summer. | Financial Aid Officer, Dean of Counseling, Director of Marketing | SD3.C.2: Completion of 15+ units per semester—decrease equity gaps for disproportionately impacted groups by 40% by fall 2023, and fully close achievement gaps by fall 2026 | Marketing Specialist |  |  | X
Hire Director of International Students and Outreach. Expand partnership with international recruiters. | Director of Outreach and International Relations | SD3.D.4: International students—increase from 105 in fall 2017 to 315 by fall 2023 | Dean of Emerging Programs, Admin Assistant for Dean, Director position |  |  | X |  |  | X
Continue efforts to reach out to industry to identify sites for additional M80 internships. For new curriculum, explore making M80 a required course similar to CNSE or Game Design. | Dean of CTE and Career Transfer Center | SD3.E.4: Internships—increase from 148 in fall 2018 to 444 by fall 2023 | Dean of Emerging Programs, Admin Assistant for Dean | [5 empty] | X
Direct mail postcards to potential Honors students. GPS orientation to include Honors. Complete curriculum on additional Honors courses. | Dean of Honors, Faculty Coordinator of Honors, Curriculum Chair | SD3.G.3: Honors students—increase from 210 in fall 2017 to 360 by fall 2023, with a focus on increasing participation by disproportionally impacted students | Marketing Specialist |  |  | X |  | X
In addition to the action items throughout this plans, complete the following actions: reach out to fall enrollees who did not register for spring; start a marketing campaign for specific for Moorpark and for specific populations like LatinX and adult learners; Market all new CTE programs, ADTs, 4 week winter session, and ESL; | Director of Outreach and International Relations, Director of Marketing, Deans and Chairs of respective areas | SD5.C.1: Meet annual FTES targets | Dean of Emerging Programs, Admin Assistant for Dean, Marketing Specialist |  |  | X |  |  | X |  |  |  | X
Conduct a feasibility study | VPAA | SD5.C.2: Contract and community education—conduct a feasibility study by 2019-2020 | Dean of Emerging Programs, Admin Assistant for Dean, Professional Expert to conduct feasibility study for contract and community education | [5 empty] | X |  |  | X
Expand ESL and Makerspace program offerings. | Dean and Chair of ESL, Dean of CTE, Director of International Students and Outreach | SD5.C.3: Noncredit FTES—Increase to 91 by fall 2023 | Dean of Emerging Programs, Admin Assistant for Dean | [5 empty] | X |  |  | X | X

## Sheet2
 | Establish effective student check-in method within Teaching and Learning Center (TLC) using IDs and database that will assist TLC staff to provide academic student support workshops to our DI students
 | Increase use of drop-in and appointment tutoring by equity-related programs (Vet Resource Center, Athletics, Foster Youth, ACCESS, and EOPS)
Activity: Enhanced tutoring services