Guided Pathways Liaison Update April 12, 2019

* Faculty/staff/administrators met with consultants Rob Johnstone and Priya Chaplot April 11, 2019
* Metamajors Design Team
	+ Metamajors is officially “Areas of Interest”
	+ There are 8 Areas of Interest, including “Exploratory” for undecided majors.
	+ Each program is organized into one or two Areas of Interest.
* Program Mapping Design Team
	+ Currently, approximately 20 programs have organized mapping teams or have begun mapping.
	+ Several teams are scheduled to meet Flex Day (April 25 1:00-2:30) for their initial meeting. Teams who have already begun mapping are invited to use this opportunity to finalize maps.
* Student Support Design Team
	+ Design team wants to improve onboard experience, especially for students who need direction
	+ Design team considering surveys to find students’ needs. Determining optimal way to deliver survey.
	+ Consultants impressed with MyNav and encourage increased access to it
* Dual Enrollment Design team has two objectives: 1. dual enrollment 2. career education alignment. Mary and Lisa are looking for faculty as a co-chair.
* Scale of Adoption self-assessment
	+ Tentative timeline (Note: A memo received 4/12 indicates the Chancellor is allowing deadline extensions on the equity plan and goal setting documents)
	+ 4/9 GPSC meeting review and input
	+ 4/11 Review with consultants
	+ 4/15 Webinar on reporting and how to file extensions
	+ next week: conference call with regional coordinators
	+ 4/16 Academic senate review and input
	+ 4/16-4/24 classified senate review and input
	+ 4/24 Progress report to VPs/Pres for review and input
	+ May GP Faculty leads finalize report, preparing for September version
	+ late May present progress report to consultation conference
	+ Summer Coordinate with IR to align with Vision for Success (?)
	+ Aug Flex week session to review and finalize progress report
	+ Aug/Sep Academic Senate reviews September version of progress report
	+ Aug/Sep Classified Senate reviews September version of progress report
	+ Aug/Sep Deans Council review September version of progress report
	+ Sep. 30, 2019 Submission of Progress report