**GUIDED PATHWAYS SCALE OF ADOPTION, SELF-ASSESSMENT**

**PROPOSED TIMELINE**

* 4/9 Steering Committee Brain-Dump
* 4/11 Consultant Review and Guidance
* Next Week GP Liaisons’ Conference Call (to ensure we have enough information and guidance)
* 4/16 Initial Academic Senate Review of our Draft
* 4/16-4/24 Email report to Classified Senate for review and input (when is their next meeting)
* 4/24 Deans Council review of and input for initial progress report
* 4/24 Email draft progress report to VPs/Pres for review and input
* May GP Faculty Leads finalize our report, preparing for September version
* Late May Present progress report to Consultation Conference
* Summer Coordinate with IR to align with Vision of Success (?)
* Aug Flex Week Flex Session to review and finalize progress report
* Aug/Sept Academic Senate reviews our September version of progress report
* Aug/Sept Classified Senate reviews our September version of progress report
* Aug/Sept Deans Council review our September version of progress report
* Sept 30th Submission of Progress Report