## Planning Agendas
Planning Agenda Item | Responsible Party | Anticipated Completion Date | EdCAP 9/27/2011 & Comments | EdCAP 10/25/2011 & Comments | EdCAP 11/22/2011 & Comments | EdCAP 1/24/2012 & Comments | EdCAP 2/28/2012 & Comments | EdCAP 3/27/2012 & Comments | EdCAP 4/24/2012 & Comments
Revise the Program Plan Template, making explicit the connection between Strategic Objectives and resources requests, including personnel, operations, facilities and technology areas. [Standard IB.3] | Ed CAP - Lead. Tech CAP, Facilities CAP, Fiscal Planning Committees | 2012-01-31 | Criteria and information needed being assembled. Awaiting developments in other areas for complete list. |  |  | Done. Template has specific places where programs can site the connection of their request to the strategic objectives
Beginning 2010-2011, the Office of Business Services will report back to units on allocations made and deferred in preparation for planning in the subsequent year. [Standard IB.4] | Office of Business Services | Spring 2011 | These reports began last fiscal year. They are now an ongoing practice.
Complete the following tasks by 2012 to reach Sustainable Continuous Quality Improvement in the implementation of student learning outcomes: | Programs / Program Faculty; Institutional Researcher | 2012-12-31 | On track for completion
 Complete the second assessment cycle of the degree and certificate program outcomes. | Programs with degrees and certificates | 2012-12-31 | Programs need to develop degree and certificate outcomes. A place for reporting will be added to program plan template.
 Complete the first assessment cycle of the general education outcomes. | Programs with general education courses; Curriculum Committee | 2012-12-31 | General Ed. outcomes have been identified. Courses need to be identified.
 Identify student learning outcomes for core competencies, and complete the first cycle of assessment. [Standard IIA.1(c)], [Standard II.A.2(b)] and [Standard II.A.2(i)] NB: core competencies = institutional outcomes | All instructional programs | 2012-12-31 | Draft of institutional outcomes is being vetted by Academic Senate.
Implement and sustain the 5-year staggered cycle of curriculum review beginning 2010, and document the curriculum review status on Program Plans. [Standard II.A.2(a)] and [Standard II.A.2(e)] | Curriculum Committee | Schedule in place by Fall 2010; first 5-years of cycle completed by May 2015 | 5-year review cycle was implemented Fall 2010. Curriculum status was noted on program plans beginning Spring 2011. Five year cycle is ongoing. | The Curriculum Committee has had a very collegial and productive 200/2011 academic year. With great flexibility, we responded to changes in curriculum at State and local levels. The first year of our five year cycle has been successfully completed which included Anthropology, Work Experience, Chicano Studies, Photography, Geography, Geology, GIS, Graphic Design, Counseling, Environmental Science, Economics and Dance. There are a few CORs from various Depts that are still lagging behind but most of the Departments did a stellar job.
Complete review of general education program in 2010-2011 and identify core sequences for disciplines within each general education category. [Standard II.A.2(c)] and [Standard II.A.3] | General Education working group of Curriculum Committee | 2012-12-31 | GE working group has created outcomes. In process of reviewing GE courses against the outcomes. | There has been extensive training on the use of Curricunet in curricular development and in it's use for monitoring SLOs for courses and programs. GEOs were recommended to Academic Senate and a modification to the current GE program was discussed.
Complete the District policy and administrative procedure on program discontinuance. Align college local practice on program status review to comply with anticipated District policy and administrative procedure. [Standard II.A.6(b)] | DCSL; Academic Senates | December 31, 2011? | District policy is in DCSL for consideration. |  |  | Done. Local practice approved on ____.
Through venues of faculty professional development, the College will more widely disseminate the concept of distinguishing personal conviction from accepted professional views within a discipline. [Standard II.A.7(a)] | Faculty Development Committee | 2012-05-31 | To be agendized at next Faculty Development meeting
Develop cluster outcome assessment methodology and implement in 2011-2012. [Standard IIB.1] and [Standard IIB.4] | Institutional Research, Student Services Council, Student Service Programs | 2012-05-31 | MyNAV work group has assessed outcomes for one level of engagement; development of measures for remaining levels in progress. Futures Day has assesed outcomes. Results discussions in progress.
Formally assess extra-curricular programs and their effectiveness in encouraging personal and civic responsibility, as well as intellectual, aesthetic, and personal development. [Standard IIB.3(b)] | Dean over Student Life; Office of Student Learing; Student Activities Office; and Honors Program, Year Of, Multicultural Day, and OCOB committees | 2012-05-31 | "Year of" is measuring outcomes at all events; Multicultural Day will begin discussion soon.
Develop and implement a survey to assess student engagement and satisfaction with the Counseling Department. [Standard IIB.3(c)] | Counseling Dept. | 2012-12-31
Assess Multicultural Day and One-Campus, One-Book activities for currency and effectiveness at promoting the understanding of diversity in all forms. [Standard IIB.3(d)] | Office of Student Learning; Year Of, Multicultural Day, and OBOC committees | 2012-05-31 | "Year of" is measuring outcomes at all events; Multicultural Day will begin discussion soon.
Add the element of diversity into the Moorpark College Student Perception Survey in the next cycle. [Standard IIB.3(d)] | Institutional Researcher | 2012-05-31 | District survey.
Conduct a focused dialogue regarding assessment and placement in English and Mathematics. [Standard IIB.3(e)] | Office of Student Learning; English Dept.; Math Dept.; Matriculation Committee | English: __________ Math: June 1, 2012 | Math Department cannot access self-placement information because no data is collected. Math Department is pilot testing a placement test this semester across all levels of math classes. |  |  | Math Dept. piloted using the placement test for students who did not have transcripts demonstrating completion of pre-requsisites for Spring enrollment.
Complete the hiring of a third full-time Librarian by Fall 2010. [Standard IIC.1(a)] | Office of Student Learning; Library | 2010-08-01 | Following faculty prioritization process.
Complete the reciprocal privileges arrangement with Ventura College and Oxnard College, and increase the availability of library material for students across the District. [Standard IIC.1(a)] | Library; Office of Student Learning | 2012-05-31 | 3 colleges are in process of sharing Ex-Libris and Voyager.
Continue to assess information competency of students, both within Library instruction and in the context of instruction in English and other disciplines requiring information research. [Standard IIC.1(b)] | Library; English Dept.; General Education working group | 2012-05-31 | Assessment developed and data is being collected.
Complete the re-organization of the College driven by the loss of two Academic Deans, and review the medium-term impact of the re-organization at the end of 2011-12. [Standard IIIA.2] | Office of Student Learning; President | 2013-05-31 | Continuing assessment
The Office of Student Learning, in collaboration with the Faculty Development Committee, will review the curriculum and the implementation strategy of New Faculty Orientation to ensure currency and effectiveness. [Standard IIIA.5(b)] | Office of Student Learning; Faculty Development Committee | 2011-05-31 | Completed in spring. The process will be repeated this year.
The Emergency Operations Committee will review the Emergency Incident Task List generated after the debriefing of the 2009 Guiberson Fire. An operating plan will be developed based on this review. The operating plan, once implemented, will be updated evaluated regularly for updates. The plan and its subsequent updates will be reported to District Emergency Management for overall coordination. [Standard IIIB.1(b)] | Office of Business Services; District Emergency Management | Fall 2010 | Work is completed and documented. Workplan handed off to district. Awaiting district feedback.
Provide training to faculty and staff on accessibility technology. [Standard IIIC.1(b)] | Instructional Technologist | 2012-06-30 | Online Accessibility Guide completed August 16, 2011. Accessibility training conducted Flex week Fall 2011. 2 additional accessibility workshops scheduled for Fall 2011. | 3 “Online Accessibility Basics” training sessions in calendar year so far have had 15 attendees. Universal Design concepts and accessibility tips have been added to all Desire2Learn trainings, Wimba trainings, and Online Pedagogy trainings. 4 Distance Education Captioning and Transcription Grant projects are in progress, one is completed. |  | The instructional technologist continues to offer accessibility training . Captioning was completed on 3 courses in fall. More courses are being captioned this spring.
Strengthen the feedback process from the Vice President of Business to TechCAP regarding the details of budget/item allocations at the end of each annual program planning cycle. As one cycle ends and the next begins, the Vice President of Business Services will communicate back to the programs and the College the final list of resources allocated, and items that have been tabled. In cases of non-allocation, needs must be re-examined and incorporated into the next year’s plan. The mechanism for this feedback loop exists, and will be used in the next planning cycle. [Standard IIIC.1(d)] | Office of Business Services; Tech CAP; TRAC Work Group | 2011-05-31 | Reports were made in Spring 2011. Report out during the first the Tech Cap and Fiscal Planning Committee meetings institutionalized in Fall 2011. Reports are posted online in public meetings.
Improve the Program Plan Template to specifically address the impact of prior year budget allocation/increases on goal implementation. [Standard IIID.1(a)] | Ed CAP | 2012-06-30 | This is tied to agenda #1. Criteria and information needed being assembled for program plan template revision.
Promote greater understanding and transparency in the budget development process by continuing to host Town Halls and similar forums. Continue to monitor the level of engagement and satisfaction of employees with subsequent surveys for comparison. [Standard IIID.1(d)] | Office of the President; Vice Presidents' Council | 2014-05-31 |  |  |  | Budget town hall for Fall 2011 was held on____. | Accreditation town hall was held on Feb. 16.
Revise the document Making Decisions at Moorpark College 2008-2010 by adding a companion timeline to the program planning process that more clearly articulates the budget building component of planning. [Standard IIID.1(d)] | Office of the President; Vice Presidents' Council; Academic Senate President/Council | 2011-12-31 | Revision posted on MyVCCCD for employee comment.
The Business Services Division will complete the development of a “Balanced Scorecard” as a performance planning and resource management tool, and complete the first cycle of evaluation based on the new tool by the close of fiscal year 2011-2012. [Standard IIID.3] | Office of Business Services; Institutional Research | 2012-06-30 | Scorecard has been created. First survey sent to students and results collected. Survey of faculty and staff will be completed in November.
Develop a process to evaluate the effectiveness of the Fall Fling agendas and activities in advancing the College’s planning efforts. [Standard IVA.5] | Office of the President | 2011-12-31 |  | Fall Fling was held on Oct. 7. Evaluation in progress.
The Human Resources Department will develop an equal employment opportunity plan based on the Model Equal Employment Opportunity Plan provided by the California Community Colleges Chancellor’s Office. The plan will contain specific plans and procedures for ensuring equal employment opportunity. [Standard IIIA.4(b)] | District HR; DCHR
The Chancellor will provide more staff information to Trustees regarding the broader District needs and implications of staff recommendations in order to diminish fractional or narrowly focused decision-making. [Standard IVB.1(a)] | Chancellor
The employees will be surveyed again to assess the degree to which the implementation of Board Policy 2434 has diminished the perception that the Board can occasionally stray from its policy role into operational matters. [Standard IVB.1(b)] | Chancellor
The Board will designate a review cycle to ensure that all policies and procedures continued to be revised in a timely manner. [Standard IVB.1(e)] | Chancellor
Board education will continue in the form of orientations, training sessions, and conference attendance. [Standard IVB.1(f)] | Chancellor
The survey of the Board will be distributed in July 2010, in accordance with established procedure. The data will be compiled in August 2010, and an agendized discussion of the findings will take place in September 2010. [Standard IVB.1(g)] | Chancellor
An administrative procedure will be developed to support the implementation of Board Policy 2715 Board of Trustees Code of Ethics. [Standard IVB.1(h)] | Chancellor; Board of Trustees
Conduct regular reviews of new and revised Board Policies and Administrative Procedures with College managers to ensure understanding and compliance. [Standard IVB.2(c)] | Chancellor; Board of Trustees
The Board will communicate its expectations of educational excellence and integrity by adopting more and strengthened policies in the following areas: associate degree and certificate credit requirements; credit hour limits for associate degrees and career certificates; discontinuance of programs and courses for which have not been regularly offered. [Standard IVB.3(a)] | Board of Trustees
The Board will develop a policy and procedural mechanism to review tenure recommendations where disagreements exist between College administration and tenure committees. [Standard IVB.3(a)] | Board of Trustees
In order to enhance the effective operation of the colleges, the District Human Resources Division will review its HR Toolbox for strengthened and consistent user-friendly guidelines in approaching standard employment activities, such as hiring, employee classification, and evaluation. [Standard IVB.3(a)] | District HR; DCHR
The Human Resources Division will establish and keep reasonable timelines for basic, ongoing, and repetitive functions, such as recruitment and testing, evaluation, and termination. [Standard IVB.3(a)] | District HR; DCHR
By Spring 2011, a data driven program review system for assessing all District services, DTRW, and DCSL will be implemented. [Standard IVB.3(b)] and [Standard IVB.3(g)] | Chancellor
The Board will adopt strengthened academic and program standards through collegial consultation with the Academic Senates informed by local administrative perspectives. [Standard IVB.3(e)] | DCSL; Academic Senates; Board of Trustees
Recommendations from the three independent colleges pertaining to faculty academic and professional matters will contain comment from appropriate campus administrators and Presidents regarding the adequacy of proposals. [Standard IVB.3(e)] | President; Executive Vice President
Administrative oversight of faculty proposals within DCSL and DTRW will be strengthened by assessing them for overall effectiveness in meeting student needs. Academic matters taken to the Board for action will contain the primary recommendation of the Academic Senate and the College President or her designee, such as the Executive Vice President of Student Learning. [Standard IVB.3(e)] | Academic Senate; EVP; President
The BoardDocs system will be fully implemented by the end of the fall 2010 semester. [Standard IVB.3(f)] | Chancellor
The Office of Administrative Relations will conduct a publications audit, develop an annual report to the community or other signature publication, and create a district-wide newsletter. [Standard IVB.3(f)] | Office of Administrative Relations
An online style guide will be developed for employee access and use. [Standard IVB.3(f)] | Office of Administrative Relations
The Office of Administrative Relations will assess approaches to providing technical support necessary to maintain technological communications. [Standard IVB.3(f)] | Office of Administrative Relations
District governance bodies covered by the Brown Act will post meeting agendas and minutes on the District website for public access. [Standard IVB.3(f)] | District Committees: ATAC; DLTF; DCCC; DCAS; DCHR; DCSL; DTRW

## Recommendations
Recommendations | Responsible Party | Anticipated Completion Date | EdCAP 9/27/2011 & Comments | EdCAP 10/25/2011 & Comments | EdCAP 11/22/2011 & Comments | EdCAP 1/24/2012 & Comments | EdCAP 2/28/2012 & Comments | EdCAP 3/27/2012 & Comments | EdCAP 4/24/2012 & Comments
CR1: In order to improve institutional effectiveness, the Team recommends that the College strengthen the planning process by incorporating annual, written reports describing progress toward the achievement of institutional goals and disseminate them to college constituencies. It is further recommended that the College go beyond qualitative evaluation of its planning and program review processes by developing and using consistent quantitative effectiveness measures and feedback mechanisms to improve the processes at the program and the institutional level. (I.B.2-3, I.B.5-7, II.A.2-3) | Office of the President; Institutional Research
CR2: In order to meet the Commission’s expectation of reaching the proficiency level regarding student learning outcomes (SLO) development and assessment by fall 2012, the Team recommends that the College develop specific timelines which are disseminated and reviewed, provide written summary reports of SLO assessments and improvements, and assure that assessment results are used for course, program and institutional improvement. Additionally, the College shall ensure that in every class section, students receive a course syllabus that specifies learning outcomes consistent with those in the institution’s officially approved course outlines. (II.A.1.c, II.A.2.a-b, II.A.2.f, II.A.2.i, II.A.3, II.A.6, II.B.1, II.B4, II.C.2). | Office of Student Learning; Office of Institutional Research; Deans in the Implementation of Syllabus Distribution; Every instructional program | 2012-06-01
CR3: In order to validate effectiveness and improve student success, the Team recommends that the College complete an evaluation of its self-placement process for English and mathematics and make modifications as appropriate and necessary. This could include the consideration of using diagnostic instruments and revising placement processes. (II.B.3.e) | Office of Student Learning; English Dept.; Math Dept.; Matriculation Committee | English: __________ Math: June 1, 2012 | Math Department cannot access self-placement information because no data is collected. Math Department is pilot testing a placement test this semester across all levels of math classes. |  |  | Math Dept. piloted using the placement test for students who did not have transcripts demonstrating completion of pre-requsisites for Spring enrollment.
CR4: In order to improve effectiveness, the College should evaluate its committee structure as identified in the Making Decisions at Moorpark College document with a special focus on subcommittee charges and membership as they relate to the College’s mission. This evaluation should give consideration to the creation of an executive council/committee that has constituency representation that advises the President regarding committee recommendations. Based on the evaluation, the College should develop and implement appropriate revisions to its governance structure and document them. (IV.A.2-3) | Office of the President; Vice Presidents Council; Academic Senate (President); Classified Senate (President); Student Senate (President) | [5 empty] | Making Decisions document revised and approved on ___?
DR1: In order to meet the Standards, the District, in concert with the three colleges, shall develop clearly defined organizational maps that delineate the primary and secondary responsibilities of each, the college-to-college responsibilities, and that also incorporate the relationship of major District and college committees established to assure the integrity of activities related to such areas as budget, research, planning, and curriculum. (IV.B.3.a-b, IV.B.3.g)
DR2: In order to meet the Standard, the District, in concert with the three colleges, shall document evidence that a review of District Policies and Procedures that may impede the timely and effective operations of the departments of the colleges has taken place and that appropriate modifications are made that facilitate the operational effectiveness of the colleges. A calendar that identifies a timeline for the regular and consistent review of policies shall be developed. (IV.B.1.e)
DR3: In order to increase effectiveness, the Teams recommend that the District conduct a periodic outcomes assessment and analysis of its strategic planning and decision-making processes, leading to sustainable continuous quality improvement in educational effectiveness in support of student learning and district-wide operations. (IV.B.3)
DR4: In order to improve communications, the Teams recommend that the District assess the effectiveness of its formal communications and utilize constituency and community input/feedback data to implement improvements to ensure that open and timely communication regarding expectations of educational excellence, operational planning, and integrity continues and is enhanced at all levels of the organization. (III.A.3, IV.B.3)
DR5: In order to meet the Standard, the Board of Trustees shall complete an analysis of its self assessment pursuant to Board Policy 2745 and formally adopt expected outcomes and measures for continuous quality improvement that will be assessed and reported as a component of the immediately succeeding self-assessment. (IV.B.1.g)
DR6: In order to meet the Standards, the Board of Trustees shall establish clearly written policies and corresponding procedures to ensure that decision-making is administered by staff in an equitable and consistent manner across and within the three colleges. (III.A.3.a, III.A.4.c, IV.B.1.b-c)
DR7: In order to meet the Standards, the Board of Trustees shall assess its actions in relation to its policy making role and implement a program for ongoing Board member professional development to enhance and improve the demonstration of its primary leadership role in assuring the quality, integrity, and effectiveness of the student learning programs and services delivered by the District colleges. (IV.A.3, VI.B.1. e-g)