## Sheet1
Academic Year 2014-2015
Rough Draft of Program Plan Review Timeline
Program Plans Due |  | Sept 15, 2014
Program Evals w EVP |  | Sept 15-Nov. 15
Standing committees prioritize resources |  | mid-Sept/Oct
Faculty Prioritization |  | mid-Oct
EVP response to Departments |  | End of fall semester
Dept Response/Signature to EVP |  | End Jan
EVP Summary to EdCap Co-chairs |  | 3rd week in Feb.
EdCap Co-chairs present to EdCAP |  | Feb meeting
EdCap presents to Academic Senate |  | early March
EdCap presents to Admin Council |  | early March
Summary distributed college-wide |  | mid March
President forwards report to Chancellor |  | late March
Budget meetings with VP Bus Services |  | March
President provides list of programs for |  | Early Sept 2015
review for discontinuance
Program Disc Rec Group meets |  | late Sept/early Oct
etc….